## Sheet1
Task Number | Task Name | Duration | Status | Progress | Start Date | End Date | Predessor | Task Ownwer
1 | Initiation Stage
1.1 | Project Initiation | 15 Days | 100% | Completed | 2022-02-01 | 2022-02-15 |  | Bhanu Priya
1.1.1 | Creating Project Charter | 4 Days | 100% | Completed | 2022-02-01 | 2022-02-04 |  | Bhanu Priya
1.1.2 | Identifying key stakeholder | 3 Days | 100% | Completed | 2022-02-04 | 2022-02-07 |  | Bhanu Priya
1.1.3 | Running feasibility study | 3 Days | 100% | Completed | 2022-02-07 | 2022-02-10 |  | Bhanu Priya
1.1.4 | Assemble team and tools | 5 Days | 100% | Completed | 2022-02-11 | 2022-02-15 |  | Bhanu Priya
1.2 | Requirement Analysis | 7 Days | 100% | Completed | 2022-02-16 | 2022-02-22 |  | Keerthana Reddy
1.2.1 | Assign roles | 1 Day | 100% | Completed | 16-Feb-22 16-Feb-22 |  |  | Keerthana Reddy
1.2.2 | Interview stakeholders | 2 Days | 100% | Completed | 2022-02-17 | 2022-02-18 |  | Keerthana Reddy
1.2.3 | Gather and Document | 2 Days | 100% | Completed | 2022-02-18 | 2022-02-19 |  | Keerthana Reddy
1.2.4 | List assumption and requirements | 2 Days | 100% | Completed | 2022-02-19 | 2022-02-20 |  | Keerthana Reddy
1.2.5 | Get Approval | 2 Days | 100% | Completed | 2022-02-20 | 2022-02-21 |  | Keerthana Reddy
1.2.6 | Monitor Progress | 2 Days | 100% | Completed | 2022-02-21 | 2022-02-22 |  | Keerthana Reddy
2 | Planning Stage | 52 Days | 35% | In Progress | 2022-02-23 | 2022-04-16 |  | Rohini Vemparala
2.1 | Focus on Planning | 27 Days | 52% | In Progress | 2022-02-23 | 2022-03-21 |  | Rohini Vemparala
2.1.1 | Scope Planning | 5 Days | 100% | Completed | 2022-02-23 | 2022-02-27 |  | Rohini Vemparala
2.1.2 | Project Schedule | 3 Days | 100% | Completed | 2022-02-27 | 2022-03-01 |  | Rohini Vemparala
2.1.3 | Resource Planning | 5 Days | 100% | Completed | 2022-03-01 | 2022-03-05 |  | Rohini Vemparala
2.1.4 | Budget Planning | 3 Days | 100% | Completed | 2022-03-05 | 2022-03-08 |  | Rohini Vemparala
2.1.5 | Procurement Planning | 3 Days | 100% | Completed | 2022-03-08 | 2022-03-10 |  | Rohini Vemparala
2.1.6 | Risk Managmement | 5 Days | 80% | In Progress | 2022-03-10 | 2022-03-15 |  | Rohini Vemparala
2.1.7 | Quality Planning | 6 Days | 0% | Incomplete | 2022-03-15 | 2022-03-20 |  | Rohini Vemparala
2.1.8 | Communication Planning | 2 Days | 0% | Incomplete | 2022-03-20 | 2022-03-21 |  | Rohini Vemparala
3 | Design and Development Stage | 26 Days | 0% | Incomplete | 2022-03-22 | 2022-04-16 |  | Emaz Assadi
3.1 | Prototyping and Design | 13 Days | 0% | Incomplete | 2022-03-22 | 2022-04-03 |  | Emaz Assadi
3.1.1 | Define App scope | 3 Days | 0% | Incomplete | 2022-03-22 | 2022-03-24 |  | Emaz Assadi
3.1.2 | Conduct extensive research | 4 Days | 0% | Incomplete | 2022-03-24 | 2022-03-27 |  | Emaz Assadi
3.1.3 | Create User Interface | 2 Days | 0% | Incomplete | 2022-03-27 | 2022-03-28 |  | Emaz Assadi
3.1.4 | Develop Prototype | 1 Day | 0% | Incomplete | 2022-03-28 | 2022-03-29 |  | Emaz Assadi
3.1.5 | Design Test scenarios | 1 Day | 0% | Incomplete | 2022-03-29 | 2022-03-30 |  | Emaz Assadi
3.1.6 | Designing Animations | 2 Days | 0% | Incomplete | 2022-03-30 | 2022-04-01 |  | Emaz Assadi
3.1.7 | Framework for Highlevel Design | 3 Days | 0% | Incomplete | 2022-04-01 | 2022-04-03 |  | Emaz Assadi
4.1 | Development | 13 Days | 0% | Incomplete | 2022-04-04 | 2022-04-16 |  | Team 8
4.1.1 | Select Application Architecture | 3 Days | 0% | Incomplete | 2022-04-04 | 2022-04-06 |  | Team 8
4.1.2 | Back-end development | 4 Days | 0% | Incomplete | 2022-04-06 | 2022-04-09 |  | Team 8
4.1.3 | Design API | 4 Days | 0% | Incomplete | 2022-04-09 | 2022-04-13 |  | Team 8
4.1.4 | Creating Database model | 3 Days | 0% | Incomplete | 2022-04-13 | 2022-04-15 |  | Team 8
4.1.5 | Setting up Repositories | 2 Days | 0% | Incomplete | 2022-04-15 | 2022-04-16 |  | Team 8
5 | Control and Monitoring Phase | 14 Days | 0% | Incomplete | 2022-04-17 | 30-Apr-022 |  | Srijan
5.1 | Testing | 10 Days | 0% | Incomplete | 17-Aspr-22 | 2022-04-26 |  | Srijan
5.1.1 | Release Planning | 2 Days | 0% | Incomplete | 2022-04-17 | 2022-04-18 |  | Srijan
5.1.2 | Sprint Planning | 2 Days | 0% | Incomplete | 2022-04-18 | 2022-04-19 |  | Srijan
5.1.3 | Test analysis | 3 Days | 0% | Incomplete | 2022-04-19 | 2022-04-21 |  | Srijan
5.1.4 | Testing | 4 Days | 0% | Incomplete | 2022-04-21 | 2022-04-24 |  | Srijan
5.1.5 | Automation Testing | 0 Days | 0% | Incomplete | 2022-04-24 | 2022-04-24 |  | Srijan
5.1.6 | Automation of Testing activities | 0 Days | 0% | Incomplete | 2022-04-24 | 2022-04-24 |  | Srijan
5.1.7 | Regression Testing | 2 Days | 0% | Incomplete | 2022-04-24 | 2022-04-25 |  | Srijan
5.1.8 | Configuratoion Management | 2 Days | 0% | Incomplete | 2022-04-25 | 2022-04-26 |  | Srijan
6 | Closing Phase | 4 Days | 0% | Incomplete | 2022-04-27 | 30-Apor-22 |  | Ujwal
6.1 | Deployment and Maintenance | 4 Days | 0% | Incomplete | 2022-04-27 | 2022-04-30 |  | Ujwal
6.1.1 | Business area | 1 Day | 0% | Incomplete | 2022-04-28 | 2022-04-29 |  | Ujwal
6.1.2 | Application server and clients | 1 Day | 0% | Incomplete | 2022-04-29 | 2022-04-30 |  | Ujwal
6.1.3 | Maintenance |  | 0% | Incomplete |  |  |  | Ujwal