## Estimated Costs
Estimated Project Costs
|  | PROJECT TASKS | LABOR HOURS | LABOR COST ($) | MATERIAL COST ($) | TRAVEL COST ($) | TOTAL PER TASK
| PROJECT DESIGN | Develop Functional Specifications | 82 | 10500 | 11000 | 11500 | 33082
|  | Develop System Architecture | 110 | 12500 | 10000 | 12300 | 34910
|  | Develop Preliminary Design Specification | 100 | 11500 | 14500 | 13700 | 39800
|  | Develop Detailed Design Specifications | 110 | 13500 | 12000 | 15200 | 40810
|  | Develop Acceptance Test Plan | 120 | 14500 | 15000 | 16800 | 46420
|  | Subtotal | 522 | 62500 | 62500 | 69500 | 195022
| PROJECT DEVELOPMENT | Develop Components | 110 | 17000 | 14000 | 12630 | 43740
|  | Procure Software | 140 | 15000 | 25000 | 16000 | 56140
|  | Procure Hardware | 95 | 16000 | 20000 | 14410 | 50505
|  | Development Acceptance Test Package | 110 | 17875 | 14500 | 16000 | 48485
|  | Perform Unit/Integration Test | 130 | 18000 | 15000 | 18000 | 51130
|  | Subtotal | 585 | 83875 | 88500 | 77040 | 250000
| PROJECT DELIVERY | Install System | 85 | 16000 | 15000 | 14800 | 45885
|  | Train Customers | 90 | 16500 | 16400 | 16900 | 49890
|  | Perform Acceptance Test | 90 | 17300 | 18000 | 17100 | 52490
|  | Perform Post Project Review | 95 | 18500 | 17000 | 16030 | 51625
|  | Provide Warranty Support | 0 | 0 | 0 | 0 | 0
|  | Archive Materials | 50 | 15000 | 16900 | 18200 | 50150
|  | Subtotal | 410 | 83300 | 83300 | 83030 | 250040
| PROJECT MANAGEMENT | Customer Progress Meetings/Reports | 49 | 10000 | 7000 | 17400 | 34449
|  | Internal Status Meetings/Reports | 40 | 11500 | 6500 | 15900 | 33940
|  | Third-Party Vendor Interface | 50 | 16000 | 8700 | 19000 | 43750
|  | Interface to Other Internal Departments | 20 | 14900 | 6900 | 21000 | 42820
|  | Configuration Management | 90 | 15000 | 7200 | 14500 | 36790
|  | Quality Assurance | 90 | 20000 | 9000 | 13900 | 42990
|  | Overall Project Management | 120 | 10000 | 15000 | 21000 | 46120
|  | Subtotal | 459 | 97400 | 60300 | 122700 | 280859
| Subtotals |  | 1976 | 327075 | 294600 | 352270 | 975921
| Risk (Contingency) |  | 40 | 8000 | 8000 | 8079 | 24079
| Total (Scheduled) |  | 2016 | 335075 | 302600 | 360349 | 1000000

## Actual Costs
Expenditures Over Time | Actual Project Costs
|  | ITEM | COST | DATE | REASON FOR EXPENDITURE
| INSTALLATION | Install System | 45000 | 02.01.2022
|  | Train Customers | 42500 | 02.05.2022
|  | Perform Acceptance Test | 40000 | 02.10.2022
|  | Perform Post Project Review | 28000 | 02.19.2022
|  | Provide Warranty Support | 0 | 02.20.2022
|  | Achieve Materials | 10000 | 02.22.2022
|  | Subtotal | 165500
| PLANNING (RFP) | Install System | 50000 | 02.23.2022
|  | Train Customers | 50000 | 02.25.2022
|  | Perform Acceptance Test | 45000 | 02.27.2022
|  | Perform Post Project Review | 43000 | 02.28.2022
|  | Provide Warranty Support | 0 | 03.01.2022
|  | Archive Materials | 20000 | 03.02.2022
|  | Subtotal | 208000
| PLANNING 2 | Install System | 50000 | 03.03.2022
|  | Train Customers | 40000 | 03.05.2022
|  | Perform Acceptance Test | 28000 | 03.15.2022 |  | 602000
|  | Perform Post Project Review | 36000 | 03.25.2022
|  | Provide Warranty Support | 0 | 03.26.2022
|  | Archive Materials | 17000 | 03.27.2022
|  | Subtotal | 171000
| CONSTRUCTION | Install System | 54000 | 03.28.2022
|  | Train Customers | 57000 | 03.31.2022
|  | Perform Acceptance Test | 39000 | 04.04.2022
|  | Perform Post Project Review | 58000 | 04.14.2022
|  | Provide Warranty Support | 0 | 04.15.2022
|  | Archive Materials | 15000 | 04.16.2022
|  | Subtotal | 223000
| TEST & DELIVERY | Install System | 46500 | 04.17.2022
|  | Train Customers | 50000 | 04.20.2022
|  | Perform Acceptance Test | 40000 | 04.26.2022
|  | Perform Post Project Review | 50000 | 04.28.2022
|  | Provide Warranty Support | 20000 | 04.29.2022
|  | Archive Materials | 25000 | 04.30.2022
|  | Subtotal | 231500
| PROJECT TOTAL |  | 999000 | 05.01.2022

## Data Worksheet
Project Data Worksheet
| WEEK | PROJECTED WEEKLY COST | ACTUAL WEEKLY COST | PROJECTED CUMULATIVE COST | ACTUAL CUMULATIVE COST
| 1 | 68000 | 57000 | 68000 | 57000
| 2 | 65000 | 53500 | 133000 | 110500
| 3 | 62000 | 55000 | 195000 | 165500
| 4 | 71394 | 86000 | 266394 | 251500
| 5 | 77391 | 85000 | 343785 | 336500
| 6 | 82391 | 84000 | 426176 | 420500
| 7 | 68391 | 87000 | 494567 | 507500
| 8 | 73391 | 88000 | 567958 | 595500
| 9 | 77791 | 86000 | 645749 | 681500
| 10 | 73391 | 86000 | 719140 | 767500
| 11 | 141430 | 111500 | 860570 | 879000
| 12 | 139430 | 120000 | 1000000 | 999000
|  | 1000000 | 999000

## Cumulative Project Costs
Projected vs. Actual Costs Diagram
MONTHLY COST
CUMULATIVE COST