## Sheet1
Project Risk Analysis
Risk Number | Status | Risk Name | Description | Likelihood of Occurrence (1-5) | Impact (1-5) | Ease of Detectability (1-5) | Risk Priority Number | Date Opened | Risk Owner | Date Closed
5 | Progress | Financial Threats | Budgetary control and effective costs place a crucial role in creating an smartphone application. | 5 | 5 | 5 | 125 |  | Keerthana
16 | Incomplete | Uncontrollable platform risk | The greater risk of mobile development application is the risk of investing in a platform over which one has no control over. | 4 | 4 | 5 | 80 |  | Ujwal
18 | Complete | Management resource risk | Lack of management required to handle technological requirements or short staffed | 4 | 4 | 5 | 80 | 2022-03-14 | Bhanu | 2022-03-14
2 | Complete | Risks Associated with Communication | To create a software solution that fits all of the needs, there must be clear communication between the customer and the programmer. | 4 | 4 | 4 | 64 | 2022-03-05 | Bhanu | 2022-03-06
24 | Incomplete | Regulation change risk | Regulatory compliance changed after the application is deployed in the marketplace | 4 | 4 | 4 | 64 |  | Srijan
1 | Complete | Risks Associated with Clients | Due to the lack of customer's technical expertise leading to an | 5 | 4 | 3 | 60 | 2022-03-01 | Rohini | 2022-03-03
3 | Incomplete | Market Risks | Product which dosen't meet the market demands or satisfy client requirements. | 5 | 4 | 3 | 60 |  | Srijan
4 | Progress | Risks Associated with the Resources | Dependency on Resources, Platform, investment by stakeholder's. | 5 | 4 | 3 | 60 |  | Emaz
13 | Incomplete | Incorrect software provider | Selecting an outsouring application development partner without any experience may lead to derailing the project deliverables causing delays. | 3 | 4 | 5 | 60 |  | Emaz
14 | Progress | Security Risk | Risks associated with security issue surrouding the data and privacy of the application. | 4 | 5 | 3 | 60 |  | Rohini
22 | Complete | Reverse engineering risk | Modifying source code posing severe security risk | 5 | 4 | 3 | 60 | 2022-03-15 | Bhanu | 2022-03-17
23 | Complete | Authorization and authentication risk | Executing functionalities by attackers on the server side of the application | 4 | 5 | 3 | 60 | 2022-03-19 | Emaz | 2022-03-19
25 | Complete | Bugs/crash report risk | Improper identification of bugs or crash reports | 5 | 3 | 4 | 60 | 2022-03-20 | Rohini | 2022-03-21
6 | Progress | Technological related concerns | Technical risks are mostly associated with Algorithm, Platform, Graphical User Interface and stragegies used for testing. | 4 | 4 | 3 | 48 |  | Ujwal
10 | Incomplete | External Risks | Certain programs make advantage of GPS, whereas the majority of them require access to the internet to function. | 4 | 3 | 4 | 48 |  | Emaz
12 | Complete | Unmanageable subscriber growth | Unexpected user growth leading to application downtime . | 4 | 4 | 3 | 48 | 2022-03-10 | Srijan | 2022-03-12
19 | Progress | Post launch risk | Lack of proper planning for long term sustainability as business model and or Return on Investment | 5 | 3 | 3 | 45 |  | Srijan
11 | Complete | Schedule Risk | The cause is due to inability to fulfil deadlines . | 5 | 4 | 2 | 40 | 2022-03-08 | Bhanu | 2022-03-09
20 | Progress | Product strategy risk | Improper framework for application development leading to poor vision | 4 | 2 | 5 | 40 |  | Rohini
15 | Complete | App store denial risk | Not considering the terms and conditions of the marketplace for users to download . | 3 | 3 | 4 | 36 | 2022-03-12 | Keerthana | 2022-03-13
21 | Progress | Insecure data | caused by inadequate of processes to manage the cache of keystrokes, pictures, and information. | 2 | 4 | 4 | 32 |  | Ujwal
17 | Complete | Single platform risk | Focusing the application development in a specified marketplace and or native app store. | 3 | 5 | 2 | 30 | 2022-03-11 | Emaz | 2022-03-12
8 | Incomplete | Risks associated with performance | Running unsecure mobile software entails significant hazards, which should be addressed immediately.To constantly checking on data breaches, the software program must use increased security check methods. | 3 | 3 | 3 | 27 |  | Bhanu
7 | Progress | Administrative Risks | Due to the time constraints, certain situations are not explored and cyber threats. | 4 | 3 | 2 | 24 |  | Rohini
9 | Incomplete | Risks Associated with Maintenance | There are dangers linked with the launching that must be addressed as soon as possible. | 2 | 2 | 2 | 8 |  | Srijan
2. Provide a risk mitigation strategy for each risk
Risks Asoociated with Clients: | Developing a product based on the needs of the clients by understanding, documenting and analyzing their requirements of the product which was going to launch.
Risks Asoociated with communication | Proper effective communication regarding the design and software application used is important by incorporating adequate amount of time with team mates to minimize the occurance of errors due to fatal designs
Market Risks: | Coming up with a product which had the appropriate market needs, adequate new and appropriate features by analyzing the competitive products which were currently in the market.
Risks Associated with the Resources: | Trying to have the support from stakeholders as they play a major role in granting funds, having skilled professionals to complete the technique sensitive tasks, and building a correct platform, background and security checks before the product is released into the market.
Financial Treats: | Proper estimatioin of budget in the planning phase, and having adequate buffer amount in anticipation of financial crisis.
Uncontrollable platform risk | Diversification and channel ownership can assist to limit platform risk. Being on multiple platforms allows you to minimize your platform risk.
Management resource risk | Management resource risk can be eliminated by planning ahead of time and evaluating the organization's resource allocation plan, as well as addressing any potential concerns.
Regulation change risk | Regulation change risk can be minimized as change is inevitable, make sure your team is prepared for it and has enough time to react through team meetings, scheduling tools, or additional trainings.
Incorrect software provider | Checking the reliability of the software that the organization uses or plans to utilize can help you avoid selecting the wrong software and determine what the consequences are if the software fails.
Security Risk | Always use the most updated security fixes, regularly train your workforce on cybersecurity risks. To reduce security risks, encrypt your data and restrict login attempts.
Reverse engineering risk
Authorization and authentication risk | If the authorization appears strange or suspicious, the user will be required to complete further steps to acquire access. We can also add additional security measures such as biometrics.
Bugs/crash report risk | Encrypt your data and limit login attempts to reduce software risk. Improve the code quality.
Technological related concerns | Computers and servers must all be monitored. Keep your software up to date by updating it to the most recent version. For backup files, remote or offline storage should be used.
External Risks | Don't depend entirely on one type of customer. Dealing with natural disasters Examine whether or not it is best to acquire insurance to protect against weather or other calamities.
Unmanageable subscriber growth
Post launch risk | All of these can assist you in avoiding post-launch risk. - Prepare in advance for inefficiency. Prepare the test framework that is updated regularly. Initiate contact with your customers.
Schedule Risk | To avoid Schedule Risk, create a simple shared calendar that is effective enough to balance the project's scale and complexity.
Product strategy risk | Smaller batch sizes, better resource utilization, distinctive features, and a a clear focus on a single project can all help minimize Product strategy risk.
App store denial risk | Follow the rules. Incorporate appropriate meta data. Include a Privacy Statement on your website. Find and patch the vulnerabilities to prevent being rejected access to the App Store.
Insecure data | Implement end-to-end encryption, reduce data surface area, and use anti-malware protection to eliminate the risk of insecure data.
Single platform risk | By diversifying your outlets and audience, you can ensure that your entire business hustle is not jeopardized if one platform fails.
Risks associated with performance | Act promptly to avoid disrupting the flow of a project. To avoid performance-related risks, develop risk protocols to aid in better coordination, communication, and reporting.
Administrative Risks | General administrative responsibilities such as rosters, which decrease exposure, and policies and operating procedures, which specify work practices and protections for a process, should be conducted and monitored efficiently.
Risks Associated with Maintenance | Identify potential risks or hazards , Plan ahead of time to foresee and effectively manage, and take risk management decisions at the correct scale.

## Sheet2
Prioritize your risks according to their RPN
Risk Name | Risk Priority Number
Financial Threats | 125
Uncontrollable platform risk | 80
Management resource risk | 80
Risks Associated with Communication | 64
Regulation change risk | 64
Risks Associated with Clients | 60
Market Risks | 60
Risks Associated with the Resources | 60
Incorrect software provider | 60
Security Risk | 60
Reverse engineering risk | 60
Authorization and authentication risk | 60
Bugs/crash report risk | 60
Technological related concerns | 48
External Risks | 48
Unmanageable subscriber growth | 48
Post launch risk | 45
Schedule Risk | 40
Product strategy risk | 40
App store denial risk | 36
Insecure data | 32
Single platform risk | 30
Risks associated with performance | 27
Administrative Risks | 24
Risks Associated with Maintenance | 8